## Gap Analysis
Severe Hypertension in Pregnancy Patient Safety Bundle - For Delivering Hospitals Only
|  | Item | Haven't Started Yet | Ideas are There | In Progress | Almost Completed | Completed | Action Items
Readiness - Every Care Setting | 1 | A standard protocol for maternal early warning signs, diagnostic criteria, monitoring and treatment of severe preeclampsia/eclampsia (including order sets and algorithms) | 0% | 13.04% | 13.04% | 0% | 73.91% | We are part of NPQIC and have followed all recommendations and changed policies to match evidence based practices. Policy and order set in place All chi health campuses follow standard division policy and process. We conduct audits of all severe htn cases and data is shared monthly at unit, campus and division level. Current standard orders, MEWS in discharge instructions. Algorithms located in all the OB and postpartum rooms. We have a current policy for emergent treatment of patients presenting with severe hypertension that outlines treatment and has an algo rhythm for care National team created the hypertension bundle as a resource. Market level policies and procedures and order sets. Monthly audits of all hypertension patients. Coaching to nurse and provider for all fallouts. Hypertension algorithm is available in every room and patient chart for resources. policy in place including algorithm. working on order sets. Participation in the NPQIC and AIM lead to the development of Procedures for administration of magnesium sulfate for Pre-eclampsia and premature labor, Intravenous labetalol and hydralazine administration in labor and delivery, and Nursing care of the OB patient with hypertension. Not quite meeting our goal of over 90% compliance because we have low volumes. But we have an algorithm and order set in place We utilize Epic, and in every OB admission order set there is a hard stop to address medications for maternal hypertension. There is a pathway to guide nurses in treatment. We have a policy in place. We have not joined the NPQIC hypertension bundle. We have two delivering providers and are not looking to have a standard protocol, education is shared and patient care is individualized. We have an order set built for Tocolytic/antihypertensive treatment, and policies built for tocolytic therapies (including magnesium for pre-eclampsia), but are in the process at looking at the updated AIM Maternal Hypertension and Early Warning Signs to update our processes and protocols. Other than the guidelines set out in our policies for Tocolytic Therapy (magnesium), and HELLP syndrome, we do not have an algorithm. Implementation of Order Set with Bryan Health and staff education on reporting Vital Signs and OB Hypertension EMR tools developed to identify two elevated blood pressures meeting severe range criteria, leads to an approved protocol order to administer oral antihypertensive meds. Inpatient obstetric and ED We have the algorithms available from AIM, but we do not educate to these yet. We have a policy and procedure for Pre-eclampsia , magnesium sulfate for pre-eclampsia/ post partum hypertension and PIH. . We also have order sets to help guide staff . No algorithm as of now Meetings with NPQIC to help identify gaps. Identified a physician champion to help with physician collaboration. Updated policies and order sets. Completed nursing education. Implemented chart audits.
| 2 | A process for the timely triage and evaluation of pregnant and postpartum patients with severe hypertension or related symptoms | 0% | 17.39% | 4.35% | 8.7% | 69.57% | Part of the division protocol. Met with educators and leaders of the ED as part of the process to individualize the campus process. Standard order set for nurse to follow Policy made that outlines steps for triage, medication administration and notification of provider National team created the hypertension bundle as a resource. Market level policies and procedures and order sets. Monthly audits of all hypertension patients. Coaching to nurse and provider for all fallouts. Hypertension algorithm is available in every room and patient chart for resources. ED triage, gets MSE Need to educate team members outside of OB. We have started research and looked within the system to see if there are current policies that could be used/cloned. Would also like to possibly just add to an existing policy procedure for OB triage. ER asks if a patient delivered within the last 6 week period and we are also starting to give patients bracelets upon dismissal if they have severe hypertension during their stay OB patients are 1 on 1 care in the facility and triage is completed quickly. We do not a specific policy or procedure specifically for the triage/evaluation of patients with severe HTN/related symptoms. It is a general understanding at this time that if a mother has related lab values outside the normal limits, 2 or more related vitals outside the normal limits (15 minutes apart), or signs/symptoms associated with severe HTN noted on assessment that he provider will be notified and will place orders for monitoring or treatments accordingly. We are in the process of updating this. Our policy for both OB & ED patients is that triage occurs within 30 or 15 minutes respectfully Collaboration with community providers and ED teams to ensure patients are sent to OB Triage on L&D to be evaluated during pregnancy and in the postpartum period. We have a process for evaluating and what medications to be given per order set BP every 15 minutes. Once SBP is less than 160 mmHg AND DBP is less than 90 mmHg, continue monitoring BP every 15 minutes for 1 hour, then every 30 minutes for 1 hour then every 4 hours.
| 3 | A system plan for escalation, obtaining appropriate consultation, and maternal transfer as needed | 0% | 8.7% | 13.04% | 4.35% | 73.91% | Clearly outlined in policy. Providers have good relationships and transfers of care are done relatively easily without complications Follow an escalation tree when needed. Educators provided guidance and resource. EMTALA applies Standard of care We have an existing policy "Transfer Patient Hospital to Hospital" that does touch on OB, but only in regards to safety of transfer in regard to labor/deliver, nothing on consult or escalation etc. Could edit this policy that already exists or create a new one altogether and include this among other metrics. Looking forward to the group's feedback. utilize an algorithm for care At this time the plan/system for escalation/obtaining appropriate consultation and maternal transfer is up to the discretion of the provider and is not a specific policy or algorithm. This is a project we are working on this year. We have a policy on Transfer of Obstetric Patient Prior to Delivery Policy. In all high risk deliveries our delivering providers consult Bryan Maternal Health and base care off their recommendations
| 4 | Ensure rapid access to medications used for severe hypertension/eclampsia with a brief guide for administration and dosage in all areas where patients may be treated | 10% | 0% | 10% | 10% | 70% | We have an order set that allows initial dose of hypertension medications to be on all patients med admin to initiate if needed. Order set as well as an emergency box with supplies and medications needed and process for over ride of medications in the pyxis Medications in pyxis and an HTN med box on the unit Standing order in hospital approved by med staff process. Also added on all OB order sets and is available in Pyxis on units caring for pregnant or postpartum women. Medications, including name of medication, dosage, frequency of administration and escalation of medications is clearly outlined in the policy and routine order set All available in Pyxis. Nursing has the ability in order set to administer Procardia, PO if provider not available. IN our current Maternal Severe Hypertension/Preeclampsia policy it does go over the medication admin and dosage as well as includes an algorithm. It also states: Be prepared to give anti-hypertensive medications according to provider orders Anti-hypertensive medication protocols are found within the OB Order Sets: Preeclampsia/Gest Hypertension Admit or Preeclampsia/Gest HTN Short Set. - we have this order set built into the EHR. There is also an OB order set called Preeclampsia/Gest hypertension that includes medications and interventions. The OB unit has a hypertensive emergency response medications kit available on the unit. Do we need to have this medication kit also available in the ED? Order sets for hypertension are on every OB admission type. This is a hard stop. All medications are readily available in the OB pyxis. Have emergency hypertension boxes with medications that can be placed in patient rooms when necessary
| 5 | Conduct interprofessional and interdepartmental team-based drills with timely debriefs that include the use of simulated patients | 9.09% | 9.09% | 27.27% | 4.55% | 50% | Yearly we have a pre eclampsia/ eclampsia simulation Division annually conducts drills for skills days. Unit conducts drills as needed. Have simulations scheduled twice yearly with a collaboration with other healthcare colleges Annual and Quarterly OB drills. Drill completed including nursing, RT, CRNA, MD, and ancillary. Utilized both the LDR department and surgery. Next drill should include using the ED. We hold a bi-annual skills fair and there is always an OB scenario during this mandatory training. We have done staff simulations on Maternal Hypertension and hemorrhage. We have done case studies . Bryan maternal health has been out for SIM lab and working on having Clarkson College out for education We have done staff simulations on Maternal Hypertension and hemorrhage. We have done case studies . Bryan maternal health has been out for SIM lab and working on having Clarkson College out for education
| 6 | Develop and maintain a set of referral resources and communication pathways between obstetric providers, community-based organizations, and state and public health agencies to enhance services and supports for pregnant and postpartum families | 17.39% | 4.35% | 21.74% | 8.7% | 47.83% | Between social work department and education given by nursing staff including postpartum alert materials of who to call and when to follow up after dismissal. Perinatal mood and anxiety screening on all moms and SW follow up and provider notification of elevated scores. Part of AIM and NPQIC Have a good relationship with transferring facilities and healthcare colleges. Could increase with community organizations utilize our WICI system for CommonSpirit and also NPQIC - not 100% sure on what is available in the community Our social workers keep a compiled list of all resources available in our region and share these with our patients. We have a general list of resources for Obstetric consultation and transfer processes between hospitals, but we do not have a full set of referral resources/communications pathways with community-based organizations/state/public health agencies for the general pregnant/postpartum community at this time.
| 7 | Develop trauma-informed protocols and provider education to address health care team member biases to enhance equitable care | 27.27% | 4.55% | 36.36% | 0% | 31.82% | Education given to OB staff and providers through various methods. Biannual education to providers. Respectful care education and pledge from NPQIC Unsure of what education is required for providers. Nursing education opportunities for birth equity are available but not required. OB skills day annually which includes birth equity education. Need to look into TIC training for providers and staffing. Then adjust protocols as needed. TNCC required of all Med/surg, ED, and LDR nurses. ATLS required for all providers who take ED call.
Recognition & Prevention - Every Patient | 1 | Assess and document if a patient presenting is pregnant or has been pregnant within the past year in all care settings | 13.04% | 4.35% | 43.48% | 13.04% | 26.09% | Working with NPQIC on the postpartum wristband project that is starting this month EHR notifies staff caring for patient after registration if the patient has been pregnant in the last 6 weeks. When registered the patient is asked if they are pregnant or have been recently. We have this as part of the LDR admission, but we do not have a specific question in ED charting that asks if you've been pregnant in the last year. There is last known menstrual period, but we would like to add to our triage sheet the specific question: are you pregnant or have you been within the last 12 months? looking into NPQIC bundle to get bracelets for all our PP mothers at discharge. Along with planning/preparing for educating other areas of the hospital to be alert for this (ED/Clinic) Implementing a system wide process to identify pregnant or past year. Education to come on the importance of this question.
| 2 | Ensure accurate measurement and assessment of blood pressure for every pregnant and postpartum patient | 9.09% | 4.55% | 0% | 4.55% | 81.82% | Reviewed yearly at OB skills day There is a specific postpartum patient, recovery policy. It does state: 5. Vitals and assessment every 15 minutes x 4; then every 30 minutes x 2; then every hour x 2; then if stable every 4 hours. There is blood pressure monitoring and protocol stated in the Cytotec policy. Again we have the "Maternal Severe Hypertension/Preeclampsia" policy which outlines what to do if it exists.
| 3 | Screen for structural and social drivers of health that might impact clinical recommendations or treatment plans and provide linkage to resources that align with the pregnant or postpartum person’s health literacy, cultural needs, and language proficiency | 0% | 8.7% | 21.74% | 13.04% | 56.52% | SDOH screening for all patients, preferred language assessment for all patients. Cultural needs assessments, language services for care and written discharge education given in the language the patient speaks. We do screen for the SDOH on all patients and refer to social services as needed. Have language line available for language barriers. Baby steps program Screen on admit to the Med/Surg floor and LDR department for language and cultural needs. We also have a separate intervention asking social determinants of health including safety and if they have adequate basic resources. Also ask screening questions in the admit about where baby will sleep, formula/feeding needs, if they are part of WIC etc.
| 4 | Provide ongoing education to all patients on the signs and symptoms of hypertension and preeclampsia and empower them to seek care | 0% | 9.09% | 4.55% | 9.09% | 77.27%
| 5 | Provide ongoing education to all health care team members on the recognition of signs, symptoms, and treatment of hypertension | 0% | 8.7% | 34.78% | 8.7% | 47.83% | maternal hemorrhage and hypertension are on our annual competency list Newly oriented/currently orienting OB staff are receiving specific maternal hypertension education via Methodist outreach education programs, but we are working on getting veteran OB nurses through these programs as well and making a plan to continue this education yearly. We recently just completed an OB hypertension/preeclampsia/eclampsia drill with all nurses who work in our Acute Care unit. AIM bundle will be assigned to all applicable staff that includes hypertension, sepsis, trauma care, emergency care Currently provide education on pre-eclampsia on an every 2 year basis to those who can attend. Will be providing a yearly education through an online format for ED & OB staff as well as providers
Response - Every Event | 1 | Utilize a standardized protocol with checklists and escalation policies including a standard response to maternal early warning signs, listening and investigating patient-reported and observed symptoms, and assessment of standard labs for the management of patients with severe hypertension or related symptoms | 8.7% | 13.04% | 26.09% | 8.7% | 43.48% | Working on implementing a protocol for all areas of the hospital Don't have a checklist, but are doing the actions. Work very closely with providers. Some is addressed in assessments and review of care. Everything is reported real time. Will look into policy. Maternal Severe Hypertension/Preeclampsia protocol yes, checklists and escalation policy, we need to be more specific. (The algorithm does probably cover the escalation part?) Or add to the policy. Maybe create an appendix with a checklist labor and delivery flow chart we have standard requirements for continual monitoring throughout labor EPIC assist with Maternal fetal triage index (MFTI) tool.
| 2 | Initiate postpartum follow-up visit to occur within 3 days of birth hospitalization discharge date for individuals whose pregnancy was complicated by hypertensive disorders. | 4.55% | 18.18% | 18.18% | 13.64% | 45.45% | Yes. Automatic on all patients with severe BPS. We complete chart reviews with 100% compliance Follow up is offered but not mandatory. No official plan, some providers do not buy in to this Going to work with staff on education of getting an earlier postpartum visit when hypertensive diagnosis in pregnancy. Additionally, work with our clinic to have a BP check with baby weight / color check
| 3 | Provide trauma-informed support for patients, identified support network, and staff for serious complications of severe hypertension, including discussions regarding birth events, follow-up care, resources, and appointments | 21.74% | 26.09% | 17.39% | 0% | 34.78% | Details on care on AVS including F/U appt, Maternal postpartum alert program. Include families in every debriefing for unexpected events. Collaborate with SW for resource needs. Debriefs and EAP are offered. Debriefs/critical incident debriefings are provided on an as needed basis if requested by staff. chart reviews on all level 3-4 OBs. all level 4 sent for external review. We have debrief on all labors with complications with staff involved and providers . patients are given resources based on their need level
Reporting & Systems Learning - Every Unit | 1 | Establish a culture of multidisciplinary planning, huddles, and post-event debriefs for every case of severe hypertension, which identifies successes, opportunities for improvement, and action planning for future events | 13.04% | 21.74% | 13.04% | 8.7% | 43.48% | We regularly debrief after crisis events. Discuss what went well and what did not We have a L&D Debrief Form attached to the Hypertension/Pre-e policy. Question is, does anyone do it? That needs implemented. Staff do diffusions post deliveries when needed. Drills have debriefings/hot washes to identify action planning as well Team Debriefs have been established and used regularly for bedside RN team. Continue to encourage providers to participate. Will need to also work on including the patient and support system
| 2 | Perform multidisciplinary reviews of all severe hypertension/eclampsia cases per established facility criteria to identify systems issues | 26.09% | 8.7% | 4.35% | 8.7% | 52.17% | all cases reviewed and case fallouts reviewed at perinatal committee. This would go through our standard review process and peer review criteria that is currently set up Every case of preeclampsia reviewed monthly. Regular SMM for Maternal HTN cases reviews scheduled and completed
| 3 | Monitor outcomes and process data related to severe hypertension, with disaggregation by race and ethnicity due to known disparities in rates of severe hypertension | 21.74% | 4.35% | 8.7% | 0% | 65.22% | Submitted data to the NE Perinatal Quality Improvement Collaborative. This group compiled the data and provided results. Handled by Quality department, regular part of obstetric chart reviews
Respectful, Equitable, and Supportive Care - Every Unit/Provider/Team Member | 1 | Engage in open, transparent, and empathetic communication with pregnant and postpartum people and their identified support network to understand diagnoses, options, and treatment plans | 4.55% | 0% | 22.73% | 13.64% | 59.09% | Respectful care initiatives in place. Education available in multiple languages. Just working on getting this into policy. We do this, just figuring out how to document it
| 2 | Include pregnant and postpartum persons as part of the multidisciplinary care team to establish trust and ensure informed, shared decision-making that incorporates the pregnant and postpartum person’s values and goals | 0% | 9.09% | 18.18% | 9.09% | 63.64% | Have a patient representative on Respectful Care team for Perinatal and Pediatric care. General practice, not formally written into policy Baby steps, birth plans respectful care initiatives in place
Obstetric Emergency Readiness Resource Kit - For Delivering and Non-Delivering Hospitals
|  | Item | Haven't Started Yet | Ideas are There | In Progress | Almost Completed | Completed | Action Items/ Notes
Readiness | 1 | Identify a rapid response team for obstetric emergencies | 23.53% | 11.76% | 23.53% | 2.941% | 38.24% | Put in a notification system to alert providers and staff of imminent delivery or Emergency delivery. I have identified RN's that have OB experience that are willing to respond if we have an OB present to our ER. The on-call physician is called in and they handle the case from that point forward. We also staff the ER with Paramedics, and they are a part of the response team The staff currently are participating in online education. We are in the process of updating our policies/procedures. We have checked all of our equipment to make sure it is available and functional. We have worked with pharmacy to make sure we have medications needed incase of an obstetric emergency. We are currently working to put together additional education for staff. Converted all OB Policies from delivering in-house to Shared Care/Non-delivery hospital OB Policies. Reflecting EMTALA parameters, encouraging transfer if safe and feasible for mother and newborn. Condensing multiple policies to reflect emergency management: including but not limited to Emergency Vaginal Delivery, Cesarean Section, Infant Assessment and Resuscitation. One staff member with OB experience named as the OB resource to review policies annually and create simulation activities to complete with nursing staff based on OB Emergency Drills. The OB resource is also an NRP instructor and ensures that all applicable staff stay current on their NRP certifications and neonatal resuscitation skills. Certain supplies are kept within the facility (OB Hemorrhage kit, OB Precipitous Delivery Kit, infant warmer and applicable supplies) and checked throughout the year for outdates. Unsure of what the metric is We use Clin Com to communicate out a need for more help We have several nurses on staff who have done L and D previously. We have a rapid response team. Precipitous Delivery Kit, up to date baby warmer with positive pressure ventilation system. We have a postpartum hemorrhage kit with medications as well as a Bakri Balloon. We have an infant warmer and a baby stress monitor When OB and newborn simulation trucks (through HHA) are providing education in the area, the OB resource and available staff attend to increase knowledge/experience. In progress: Creating a specific interdisciplinary team to identify the "rapid response team for obstetric emergencies." Called Code OB we are not large enough to have rapid response but we do have people on call in case of emergency when OB in house
| 2 | Protocols and procedures for activating the team are established | 20.59% | 11.76% | 26.47% | 5.882% | 35.29% | Reworked our policies to meet a non-delivery hospital. Re-did some of our hemorrhage kit to add meds to it. We have begun discussions. We currently do not have a team but it would include the provider on duty, the RN, the LPN and the paramedic. If others are needed they could be called in on an emergency basis ER Provider on-call would aid the scheduled ER nurse triage the OB patient, calling in the Airway provider on-call and anesthesia if available. All ER nurses have NRP, and a second nurse who has NRP would be available if delivery is imminent and transfer of the patient is not feasible. We use the Panhandle Alert system that calls the Rapid Response Team Not a policy yet, but considered more of a guideline or procedure. Obstetric Hemorrhage rapid response policy Uterine Rupture, care of policy Emergency Alerts - Plain Language has medical alert for activating response for anywhere in the building Trauma System policy Triage for the Emergency Department Patient
| 3 | All members of the organization are aware of how and when to activate the team | 20.59% | 8.824% | 32.35% | 2.941% | 35.29% | Using informacast to notify at a 'mass' level. We do not have a specific team set up. The team would include the staff already in-house. This would include the provider, RN, paramedic and LPN. Other staff, such as the MD and other RN's or paramedics could be called in on an emergency basis. There are protocols in place to call in the Airway personnel and ER providers. An ER nurse is always staffed in-house. An on-call schedule is available at the nurses’ station and on the intranet, and is updated with applicable schedule changes. Through meetings and trainings all personnel know to use the Rapid Response Team for OB emergencies as well as other emergencies.
| 4 | All members of the care team, including patients and their support networks, feel empowered to activate the rapid response team | 32.35% | 17.65% | 23.53% | 2.941% | 23.53% | We are constantly doing education on the process, and it is covered in new employee orientation Working on updating our policies and procedures. Selected “ideas are there,” as I don’t know if patients know they can activate a formal OB rapid response team. It would be more of a communication to the ER nurse if the patient has concerns, and then the ER nurse working closely with the Unit Secretary to notify on-call staff. Competency testing of how to care for OB and neonate done annually with staff Patients do not activate rapid response, but have access to call button. Will include the patient and family initiation of the rapid response team development and training.
| 5 | Ensure rapid access to needed medications, resources, and equipment are readily available and gathered in a single location | 5.882% | 0% | 17.65% | 8.824% | 67.65% | The medications and supplies are kept in the Infant warmer and the Pyxis in the ER Working with the pharmacy to make sure all medications are available and in our pyxis for use in an emergency situation MCHI has an OB Hemorrhage kit located in the ER Med Room, with access to Methergine and Hemabate in the refrigerators. There is also a precipitous delivery kit in the clean utility room of the ER. The infant warmer is located in nursing storage, along with a rolling cart that has extra precipitous delivery supplies and OB monitoring equipment. Omnicell All our emergent OB supplies are located in one storage area and pyxis. Due to storage constraints, supplies are not all located in a single location. However, locations are clearly marked. We have labor and delivery boxes that are taken to the OB room so all medications are in one spot and ease of access along with the order sets they belong to so staff knows how to administer
| 6 | Equipment checklist is readily available (See Appendix A)
| 7 | Established policies, procedures, and checklists are available to respond to obstetric emergencies | 9.091% | 0% | 18.18% | 15.15% | 57.58% | In the process of updating our policies and procedures regarding obstetric emergencies Currently we are working postpartum hemorrhage policy as well as getting all of our staff STABLE course. We have clear protocols and checklist for both hemorrhage and hypertension Policies: Obstetric Hemorrhage, Magnesium Sulfate admin in Ob, TXA for Obstetric Hemorrhage, On-Call Coverage- Emergency Dept/OB, Prepping for Cesarean Delivery, Cesarean Section, Maternal Severe Hypertension/Preeclampsia, Umbilical Cord Prolapse
| 8 | Rapid Response Team Protocol, Policy, or Procedure | 20.59% | 14.71% | 23.53% | 8.824% | 32.35% | Working on policies and procedures currently ER Provider on-call, Anesthesia provider, ER nurse (PALS, ACLS, NRP, TNCC certified, preferably with OB experience), second nurse who also has NRP, Airway provider. ER Provider on-call would aid the scheduled ER nurse triage the OB patient, calling in the Airway provider on-call and anesthesia if available. All ER nurses have NRP, and a second nurse who has NRP would be available if delivery is imminent and transfer of the patient is not feasible. ER Nurse would triage the OB patient and receive orders from the ER provider on-call. If delivery is imminent, the rapid response team would be called in to assist with delivery and stabilization of mother and newborn. If delivery is not imminent, the obstetric patient would be shipped to a nearby delivering facility via ground or air transportation. We currently have a rapid response policy that outlines when to call for high/low BPs, seizures, the patient just not looking right, etc Policy Resuscitation Services - this includes mention of LDR and staff Obstetric Hemorrhage includes mention of rapid response team
| 9 | Massive Transfusion Protocol, Policy, or Procedure | 21.21% | 3.03% | 9.091% | 0% | 66.67% | We have a mass transfusion protocol but we will need to update Policy in place for CAH-specific MTP, available blood products, and flow diagram for ease of use. Policy reviewed annually and discussed with staff. We cannot have a massive transfusion protocol due to lack of blood products in our facility. Annual drills with lab. And follow policy/procedures. do not have this policy/protocol/procedure, but refer to ACOG recommendations
| 10 | Blood Products and Blood Product Alternatives Protocol, Policy, or Procedure | 2.941% | 2.941% | 5.882% | 2.941% | 85.29% | Blood Products and Blood Product Alternatives available as a policy on MCN, reviewed annually Policies: Blood products Administration of, Plasma -Fresh Frozen, MTP Blood alternatives need to be added to the procedure. It has been by individual patient preferences in relation to their personalized care.
| 11 | Obstetric Hemorrhage Order Set | 14.71% | 8.824% | 11.76% | 2.941% | 61.76% | Within a postpartum order set, the Major Bleeding considerations are automatically selected to include TXA, Methergine, Carboprost, Cytotec, and Pitocin (along with dosage considerations and route of administration). Both ED and OB have postpartum Hemorrhage order sets. We have a postpartum hemorrhage labs order set as well. we have meds/orders available on CERNER, but not within 1 order set
| 12 | Obstetric Hemorrhage Checklist
| 13 | Management of Hypertension in Pregnant or Postpartum Patients Checklist | 9.091% | 9.091% | 18.18% | 15.15% | 48.48% | We do not have a checklist at this time. We will need to develop on. We do have hypertension medications available in pyxis Considerations included in "Emergency Vaginal Delivery" policy Checklist in the form of orders that come with the order set - interventions that you chart on. There is no paper check list though that you pull and check off.
| 14 | Hypertension Treatment Algorithm | 18.18% | 9.091% | 9.091% | 3.03% | 60.61% | Visual representation with an algorithm is not present, but the required information is included in the policy "Emergency Vaginal Delivery" in the Pre-Eclampsia, Eclampsia, and Hypertension section. Providers have this available on their phones, we have printed copies. Need to educate on it more for 100% awareness
| 15 | Preeclampsia and Eclampsia Management Algorithms, Protocols, and Checklists | 15.15% | 6.061% | 18.18% | 6.061% | 54.55% | Policy included in "Emergency Vaginal Delivery" in Pre-Eclampsia, Eclampsia, and Hypertension section. Additional section specifically highlighting magnesium administration and considerations. We currently have medications for preeclampsia but need protocols and checklists Algorithm, policy/protocol, order sets all there. Need to know exactly what is required of the checklist
| 16 | Magnesium Sulfate Administration Protocol, Policy, or Procedure | 9.091% | 3.03% | 3.03% | 3.03% | 81.82% | Policy included in "Emergency Vaginal Delivery" in Pre-Eclampsia, Eclampsia, and Hypertension section. Additional section specifically highlighting magnesium administration and considerations. Algorithm not present.
| 17 | Cardiovascular Disease Assessment in Pregnant and Postpartum Women Protocol, Policy, or Procedure | 48.48% | 12.12% | 6.061% | 6.061% | 27.27% | Policy included in "Emergency Vaginal Delivery" in Pre-Eclampsia, Eclampsia, and Hypertension section. Additional section specifically highlighting magnesium administration and considerations. Postpartum to discharge ongoing assessment included within the policy (including reversal agent for magnesium). Cardiac triage algorithm. We do a head to toe, probably need to add in to document a clearer cardiovascular assessment Admission procedure includes past and current history.
| 18 | Telemetry Monitoring Protocol, Policy, or Procedure | 21.21% | 15.15% | 3.03% | 3.03% | 57.58% | Not yet included within policy, but will be added to "Emergency Vaginal Delivery" in the pre-eclampsia, eclampsia, and hypertension section (specifically when administering magnesium) Admission procedure includes past and current history.
| 19 | Care for Cardiac Patient Protocol, Policy, or Procedure | 28.12% | 15.62% | 9.375% | 3.125% | 43.75% | Need to include information on cardiac management (acknowledging that MCHI providers should seek consultation with a nearby OB and/or cardiologist) within the Emergency Vaginal Delivery Policy
| 20 | Sepsis Assessment Tool Protocol, Policy, or Procedure | 9.091% | 12.12% | 12.12% | 9.091% | 57.58% | We have a Sepsis Order set, protocol, and algorithm, but it does not specifically include obstetric considerations. We use SIRS criteria Sepsis screening is part of screening automatically in EHR for every presenting patient or patient being admitted. We do have a sepsis policy but it does not specifically mention OB Med staff has a policy stating suspected sepsis should be documented or based off vitals, s/s, should be considered. Available for all patients. Need to evaluate if there needs to be any additions for pregnant or postpartum patients
| 21 | Universal Verbal Screening for Substance Use Disorder (SUD) Protocol, Policy, or Procedure | 12.12% | 6.061% | 18.18% | 12.12% | 51.52% | General Emergency Room screening in place, but it does not specifically include obstetric considerations. Part of required screening for all patients
| 22 | Pain Protocol for Patients with SUD Protocol, Policy, or Procedure | 27.27% | 18.18% | 21.21% | 6.061% | 27.27% | Numeric pain score, opioid stewardship committee in place at MCHI, dilaudid not kept in the formulary, pain clinics from Lincoln and Grand Island managing patients experiencing chronic pain, but it does not specifically include obstetric considerations. No specific procedure. Individualized care.
| 23 | Risk Assessment for Suicidal Ideation Protocol, Policy, or Procedure | 9.375% | 0% | 6.25% | 0% | 84.38% | We have a policy and a procedure, and we use virtual visits General emergency room risk assessment available for use on all patients, but does not specifically include obstetric considerations. We do Edinburgh assessment postpartum. Suicide and depression risk screening done on admission, also done again post partum, this is done in clinic as well. If they score at risk or positive in the EMR intervention, orders and interventions are automatically ordered and put in place, there is also a prompt asking which medical provider was notified of those results. We have the following policies: Suicide precautions - inpatient acute hospital, Inpatient acute hospital suicide and depression risk screen, emergency department suicide precautions, emergency department suicide room safety checklist, emergency department suicide screening, suicide screening is mentioned in the Medical Screening Exam policy for Medical Staff Done on every patient on admission
| 24 | Perinatal Mental Health Response Protocol | 33.33% | 9.091% | 9.091% | 0% | 48.48% | Postpartum depression and screening included within a nursing care plan. We have referrals in place, screen and refer as needed With Edinburgh in EPIC system.
| 25 | Established at minimum annual training on rapid response capacity for obstetric emergencies | 30.3% | 3.03% | 15.15% | 3.03% | 48.48% | We do competency day once a year for the ER which includes Emergency OB patients We are working on putting together annual education for staff. All staff take a mandatory online education session on OB emergencies and taking care of the obstetric patient Annual training to review precipitous deliveries, OB hemorrhage management, shoulder dystocia, neonatal resuscitation, preeclampsia management and magnesium for nursing staff. NRP for all ER providers, Airway Call personnel, and ER Nurses Our yearly competencies occur in October. Will implement additional OB training for all staff
| 26 | Supportive activities like routine and appropriate training of all clinical and non-clinical staff who may be involved with responding to obstetric emergencies in place | 21.21% | 6.061% | 18.18% | 6.061% | 48.48% | Annually We are in the process of putting together routine training for staff Annual training to review precipitous deliveries, OB hemorrhage management, shoulder dystocia, neonatal resuscitation, preeclampsia management and magnesium for nursing staff. NRP for all ER providers, Airway Call personnel, and ER Nurses b. Unit secretaries involved in code documentation and annual review, staff who may provide OB care are educated in setting up an infant warmer, preparing a room for delivery. AIM bundle to be assigned, all staff invited to drills, equipment training Do a great job of clinical staff, need to include nonclinical staff as well
| 27 | Team-based drills and simulations to maintain preparedness for effective recognition and response to obstetric emergencies are done regularly | 12.12% | 15.15% | 21.21% | 9.091% | 42.42% | We are working to make this happen annually We are in the process of putting together training for staff, will include drills and simulation Annual training to review precipitous deliveries, OB hemorrhage management, shoulder dystocia, neonatal resuscitation, preeclampsia management and magnesium for nursing staff. NRP for all ER providers, Airway Call personnel, and ER Nurses. This training includes team-based drills in the ER and hands-on practice with the infant warmer. We do simulation twice year.
| 28 | Plan for appropriate patient transfer to a higher level of care is in place | 0% | 3.03% | 6.061% | 3.03% | 87.88% | Transfer by air or ground protocols are in place for patients who need to be transferred to a higher level of care. Both nursing and med staff policies in place for hospital to hospital transfer
| 29 | Development of care process models for appropriate care of pregnant and postpartum people in non-obstetric care settings such as shared guidelines or algorithms | 18.18% | 9.091% | 15.15% | 6.061% | 51.52% | I would love to collaborate with other non-delivering facilities to see what shared guidelines or algorithms they have in place for obstetric emergencies. Continuing to work with ED educator on setting up drills and support education. ED has same order sets and access to policies, as does Med/Surg. Need to get hemorrhage kit in ED pyxis probably, but otherwise ED has emergency meds on checklist. Bryan Health is working on the implementation to hospital wide hypertension recognition System wide. Additional education once process is active
| 30 | Established logistics and processes for transfer are in place | 3.03% | 0% | 6.061% | 3.03% | 87.88% | Transfer by air or ground protocols are in place for patients who need to be transferred to a higher level of care. Emtala, and hospital to hospital transfer policies in place.
| 31 | Established transfer agreements are in place with facilities within the region | 9.091% | 0% | 9.091% | 3.03% | 78.79% | Yes, Grand Island OB group and Grand Island Regional/St. Francis depending on who is available and on-call, as well as bed availability. Bryan in Lincoln for newborns requiring NICU. Network agreement with CHI health Avera to Avera facility cooperation
| 32 | Appropriate transfer routes and alternate routes are determined and included in the transfer agreements | 24.24% | 0% | 6.061% | 3.03% | 66.67% | Per paramedic team or NICU transfer team from Bryan Established by ground transportation and MedAir company Transferring facility does not determine the route. This is determined by the transport crew
| 33 | Remote care capabilities and telehealth consultation supports are established | 25% | 6.25% | 9.375% | 9.375% | 50% | We have telehealth capabilities within the ER. MCHI providers would be calling GI OB/GYN for consultation for mother, Bryan in Lincoln providers would be consulted for higher NICU needs We have clear telehealth for mental health. Providers consult easily with MFM Telehealth with CUMC-BM NICU Emergency and e-ICU available Telephone consult always available with Maternal Fetal Medicine via UNMC or within the Avera System. RMOMS grant is approved and that will be a nurse monitoring our toco strips. Avel E emergency and phone with Bryan maternal health Consults with Mother fetal medicine per phone call not telerobot at this time.
| 34 | Referral resources and care coordination pathways have been established | 9.091% | 3.03% | 21.21% | 3.03% | 63.64% | We would work in close collaboration with nearby OB providers who would provide the OB patient's follow-up care, lactation visits if needed, and specialty referrals.
| 35 | Applicable staff are trained on protocols and provisions at least annually, documentation on completion of training is recorded, and staff can demonstrate knowledge | 6.061% | 12.12% | 21.21% | 3.03% | 57.58% | We are in the process of putting together training for staff Annual training to review precipitous deliveries, OB hemorrhage management, shoulder dystocia, neonatal resuscitation, preeclampsia management and magnesium for nursing staff. NRP for all ER providers, Airway Call personnel, and ER Nurses WE will be adding this to are required mandatory education and will have a completion report electronically for all staff. Yearly competencies are completed in October. Will be adding OB specific education to the competencies this year We do skills and simulation twice per year
Recognition & Prevention | 1 | Verbal screening in place for all reproductive-aged people for current or recent pregnancy in all care settings | 9.091% | 6.061% | 30.3% | 6.061% | 48.48% | Will work to educate staff on available questions within Cerner HCG if 12-50 years of age, female, and no history of sterilization. If 50-55 and still menstruating, consult with anesthesia for surgical procedures involving sedation.
| 2 | Initial assessments of acuity are utilized to triage pregnant and postpartum people presenting to the ED | 6.452% | 3.226% | 16.13% | 6.452% | 67.74% | Triage and acuity are assessed and documented within Cerner Emergency Delivery Policy outlines initial triage questions for the OB patient MSE includes full set of vitals, need to be asking specifically if they have been pregnant in the last year. Use ESI acuity in ED ED has established 15 minute triage time with acuity using the ESI
| 3 | Location of obstetric evaluation is established via facility guidelines that defines appropriate units for evaluation | 6.061% | 6.061% | 9.091% | 0% | 78.79% | Will educate staff on location of obstetric assessment within Cerner Patients will be triaged in the emergency room Greater than 22 weeks go directly to OB to be evaluated for any complaint to ED. Less than 22 weeks will stay in ED.
| 4 | Early consultation that may include telehealth with OB professionals is available for accurate triage and evaluation | 12.12% | 9.091% | 9.091% | 0% | 69.7% | We currently have telehealth, unsure if it is with OB professionals. Our providers have access to consult OB professionals as needed Professional rapport maintained with nearby OBGYN providers in Grand Island (they also maintain an outpatient specialty clinic here in Aurora twice a month) We do not have telehealth for OB emergencies. Our mid-level providers would be giving direct report via phone immediately to an OB professional. Our OB providers are on call and can receive calls from nursing and ED staff if they have concerns with triaging a new patient Telehealth is available to our patients, but currently do not have telehealth OB services r/t close proximity to large city and Maternal fetal medicine specialist.
| 5 | Screening for comorbid conditions and risk factors for maternal morbidity and mortality are completed during triage | 15.15% | 6.061% | 12.12% | 0% | 66.67% | Will need to check Cerner functionality Emergency Delivery Policy outlines initial triage questions for the OB patient Clearly included in admission assessment Look at prenatal visit information
| 6 | Patient education is provided on urgent signs and symptoms during pregnancy and postpartum and when to seek care | 9.375% | 0% | 6.25% | 12.5% | 71.88% | Education is within Cerner. Will check to make sure all information is in education form Education can be selected and discussed with patients upon discharge regarding preterm labor management and evaluation, preeclampsia signs and symptoms, OB hemorrhage/abnormal bleeding
Response | 1 | Staff is prepared for a birth in the ED | 6.061% | 3.03% | 6.061% | 12.12% | 72.73% | There are adequate policies, procedures, supplies and equipment to aid in the delivery of a newborn in the ED. pre-cip kit. Will be educating paramedics on emergency deliveries. OB staff readily available in the ED
| 2 | Routine trainings such as Basic Life Support in Obstetrics (BLSO) and Advanced Life Support in Obstetrics (ALSO) are offered to staff | 30.3% | 9.091% | 9.091% | 12.12% | 39.39% | Staff are not required to take these classes, though if they are interested in taking it the organization would support the employee. Delivering providers have taken ALSO but none of the nursing staff have done BLSO We used to have several staff that had taken ALSO but now we only have a couple that are trained due to lack of offerings in the area We are having a hard time finding ALSO classes for our staff. All delivering providers take ALSO. All staff take BLS & ACLS
| 3 | Perimortem cesarean delivery policy, protocol, or procedure in place | 51.52% | 6.061% | 12.12% | 0% | 30.3% | Will be added to the cesarean section policy We have supplies in rooms if this is needed.
New CoPs
|  | Item | Haven't Started Yet | Ideas are There | In Progress | Almost Completed | Completed | Action Items
Organization and Staff | 1 | OB services are well organized and provided in accordance with nationally recognized acceptable standards of practice for the health care of pregnant, birthing, and postpartum patients (including physical and behavioral health) | 0% | 0% | 18.18% | 9.09% | 72.73%
| 2 | Organization of the OB services are appropriate to the scope of services offered by the facility and are integrated with other departments in the facility | 0% | 0% | 0% | 13.64% | 86.36% | Want 24/7 laborist and anesthesia in-house.
| 3 | OB patient care units are supervised by an individual with the necessary education and training, such as an experienced registered nurse, certified midwife, nurse practitioner, physician assistant, or Doctor of Medicine or osteopathy | 4.76% | 0% | 4.76% | 0% | 90.48% | OB trained RN is the manager of the unit and a fellowship trained family OB is the medical director
| 4 | OB privileges are granted subject to written criteria for all practitioners providing OB care in accordance with the current requirements for hospitals and CAHs | 0% | 0% | 0% | 0% | 100% | Through credentialing.
Staff Training | 1 | Policies and procedures ensure relevant staff are trained and reflect the scope and complexity of services offered | 4.55% | 4.55% | 4.55% | 4.55% | 81.82%
| 2 | Facility has identified evidence-based, best practices, and protocols to improve the delivery of maternal care within the facility | 4.55% | 0% | 4.55% | 9.09% | 81.82% | Work with Acog, Avera System maternal medicine, OB collaborative meetings system level and locally
| 3 | New staff receive initial training | 0% | 0% | 18.18% | 0% | 81.82%
| 4 | Staff training is completed at least every two years | 0% | 4.55% | 27.27% | 4.55% | 63.64%
| 5 | Processes are in place to record staff training in personnel records and demonstrate staff knowledge on training topics identified | 0% | 9.52% | 14.29% | 0% | 76.19% | Avera learning center will track, NRP, BLS, ACLS, TNCC all recorded. OB education outside the Avera learning center is logged.
QAPI | 1 | QAPI programs are utilized to identify staff training needs, additions, revisions, or updates on an ongoing basis | 4.55% | 4.55% | 31.82% | 4.55% | 54.55%
| 2 | Data is analyzed and quality indicators are collected for the QAPI program by diverse subpopulations as identified by the facility among the OB population | 4.55% | 4.55% | 13.64% | 4.55% | 72.73%
| 3 | Data is measured, analyzed, and tracked and quality indicators on patient outcomes and disparities in processes of care, services, operations, and outcomes are monitored | 0% | 9.09% | 22.73% | 0% | 68.18%
| 4 | At least one performance improvement project is focused on improving health outcomes and disparities among the OB population annually | 13.64% | 9.09% | 9.09% | 4.55% | 63.64% | Respectful Maternal Care initiative
| 5 | OB leadership is engaged with QAPI activities | 9.09% | 9.09% | 4.55% | 4.55% | 72.73%
| 6 | A process is in place for incorporating publicly available information and data from the Maternal Mortality and Review Committee (MMRC) into the QAPI program | 36.36% | 18.18% | 9.09% | 13.64% | 22.73% | NPQIC reviews we attend NPQIC calls and participate in the AIM bundle, I believe the MMRC data is communicated through the NPQIC and we can make recommendations off of that-- so technically we could say yes, but do we actively review MMRC data on its own? No.
Transfer Protocols | 1 | Hospital has written policy and procedure for transferring patients including intra-hospital transfers of hospital inpatients | 13.64% | 9.09% | 9.09% | 0% | 68.18%
| 2 | Annual training on policies and procedures for transferring patients completed annually | 31.82% | 4.55% | 22.73% | 4.55% | 36.36% | EMTALA training Training and education incorporated into day-to-day care but not specifically provided on transfer policy and procedures.

## Appendix A
OB Checklist
Medications Ideally Stocked in ED
Anticonvulsants
Antihypertensives
Antipyretics
Atropine, Adenosine, Amiodarone
Broad Spectrum Antimicrobial Agents
Bronchodilators
Corticosteroids
Inotropic Agents
Insulin/Glucose
Lidocaine
Magnesium Sulfate
Calcium Gluconate
Naloxone
Tocolytics: Terbutaline, Nitroglycerin
Topical, Oral, and Parental Analgesics
Uterotonics: Misoprostol, Oxytocin, Carboprost Tomethamine, Methylergonovine
Tranexamic Acid
General Equipment
Electronic Fetal Monitoring (EFM) Equipment or a Handheld Doppler
Ultrasound
Electrocardiography
Pulse Oximeter
Stirrups, Equipment for Pelvic Exam Positioning
Thermometer
Blood Pressure Cuffs: All Sizes
Sterile Speculum
Urinary Catheter Kit
Flashlight if Speculums do not have a light source
Lubricating Jelly
Assorted Sizes of Sterile Gloves
Infant Warmer
Bulb Syringe
Cord Clamps
Neonatal Resuscitation Wall Chart and Flowsheet
Vascular Access
Catheter Over the Needle Device, Gauge 14-24 [14-18 gauge optimal for resuscitation]
Arterial Line if Site has Monitoring Capability
IV Administration Sets with Calibrated Chambers and Extension Tubing
Infusion Device with Ability to Regulate Rate and Volume of Infusate
Central Venous Catheters, 4.0F to 7.0F
Normal Saline
Lactated Ringers
Dextrose 10% in Water
OB Specific: Hemorrhage
Long right angle retractors
Long weighted speculum
Long needle holder
Sponge forceps (ring forceps)
Absorbable sutures
Vaginal packing options
Intrauterine balloon (i.e. Bakri, BT-Cath)
Foley catheter
B-Lynch or Uterine Compression Suture Kit
Emergency Hysterectomy Surgical Tray
Medications:
Oxytocin
Carboprost Tromethamine
Misoprostol
Methylergonovine
Tranexamic Acid
Hypertensive Disorders of Pregnancy
Blood pressure monitor, cuff sizes child to thigh
Labetalol
Hydralazine
Nifedipine
Magnesium sulfate IV/IM (can be provided IM if unable to obtain rapid IV access)
Calcium Gluconate IV
Lorazepam IV/IM (can pbe provided IM if unable to obtain rapid IV access)
Diazepam IV or Phenytoin IV
Keppra IV or PO
Urine collective device for protein/creatinine ratio or dipstick if unavailable
Cardiac Disorders of Pregnancy
Red Flags Checklist: Shortness of breath at rest, orthopnea, resting heart rate >119 bpm, O2 sat <95%
Electrocardiogram
Echocardiogram
BNP testing supplies
Toponin testing supplies
Medications:
Antiarrhythmic: adensoine, amiodarone (avoid if pregnant or lactating), flecainide, procainamide, quinidine
Nitrates
Beta Blockers: labetalol, metoprolol, propanolol, carvedilol, atenolol, sotalol
Calcium Channel Blockers: nifedipine, verapamil
Inotrope: digoxin
Diuretics: furosemide, hydrochlorothiazide
Vasdilator: hydralazine, sodium nitroprusside
Sepsis
Electronic Fetal Monitoring (EFM) Equipment
Pulse oximetry
Blood pressure monitor, varied cuff sizes
Thermometer
Foley catheter with urometer
Culture vials for blood and wound
IV fluids
Non-invasive cardiac output monitoring (stroke volume, cardiac output)
Vasopressors: Norepinephrine
Inotrope: Dobutamine
Glucose
Antipyretics: Acetaminophen and cooling blankets
Fetal lung maturity steroids
DVT prophylaxis: sequential compression device (SCD)
Antibiotics

## OB Hemorrhage Cart
Recommended Supplies | Check if Available
IV start supplies
Angiocaths
IV tubing
IV extension set
Blood product transfusion tubing
Blood warmer tubing
Urinary catheter kit with urometer
Flashlight
Lubricating jelly
Assorted sizes sterile gloves
Lab tubes: CBC, coagulation studies, etc.
Venipuncture supplies
Pressure infuser bags
Chux
Peri-pads
Vaginal packing (consider arm banding to indicate packing used)
Hemorrhage balloon and supplies
Skin marker
Syringes
Needles
Tegaderm
2x2 gauze
Adhesive bandages
Alcohol swabs
Paper tape
Cloth tape
Manual BP cuff
Stethoscope
Povidone iodine
PPE
Operating room towels
Sterile speculum
Diagrams depecting various procedures (e.g., B-Lynch, uterine artery ligation, balloon placement)
IV fluids for administration and hemorrhage balloons as your institution permits
Recommended Instruments
Set of vaginal retractors (long right angle); long weighted speculum
Sponge foreceps (minimum: 2)
Sutures (for cervical laceration repair and B-lynch)
Banjo curettes, several sizes
Long needle holder
Uterine forceps
Rapid Access Medications
Oxytocin (Pitocin)
Methylergonovine (Methergine)
Carboprost (Hemabate)
Tranexamic Acid (TXA)
Misoprostol (Cytotec)
Vaginal Birth
Vaginal retractors
Long weighted speculum
Long instruments (needle holder, scissors, Kelly clamps, sponge forceps)
Intrauterine balloon
Banjo curette
Bright task light
Procedural instructions (balloon)
Cesarean/Laparotomy
Hysterectomy tray
#1 chromic or plain catgut suture & reloadable straight needle for B-Lynch sutures
Intrauterine balloon
Procedural instructions (balloon, B-Lynch, aterial ligations)

## CoPs
Set of Requirement | Effective Date
Emergency Services Readiness | 2025-07-01
Transfer Protocols | 2025-07-01
Organization, Staffing, and Delivery of Services | 2026-01-01
Training for Obstetrical Staff in Hospitals and CAHs | 2027-01-01
Quality Assessment and Performance Improvement Program | 2027-01-01
CY 2025 Medicare Hospital Outpatient Prospective Payment System and Ambulatory Surgical Center Payment System Final Rule (CMS 1809-FC) ¦ CMS